## Vue densemble
Burndown Chart
INFOS SUR LE SPRINT |  | INFOS SUR LE SPRINT EN COURS
Champ | Valeurs
Date de début | 2022-04-26 | Date de fin du sprint | 2022-05-10
Durée du sprint (brute) | 14 | Durée du sprint (nette) | 14
Vacances | 0 | Total d'heures disponibles | 33.6
Taille de l'équipe | 4 | Total des story points | 36
Capacité maximale de l'équipe | 40% | Story points ouverts | 36
Heures de travail quotidiennes | 1.5 | Nombre d'histoires dans le sprint | 10
|  | Histoires terminées | 10
Membres de l'équipe
Kevin
Julien
Quentin
Martin
Statut
En cours
Terminé
Ouverte
Courbe de tendance

## Backlog
| Début du sprint | 2022-04-26
| Durée du sprint en jours | 14
| Vélocité | 36
Sprint ID | Backlog Item ID | StoryPoints | Story | Assigné à | Statut | Terminé le | Jour de sprint | Colonne auxiliaire | StoryPoints2 | Dernière Maj | Jour de sprint2
4 | 1 | 1 | Group page : see group movies | Quentin | Terminé | 2022-05-07 | 11 | y | 1 | 2022-05-07 | 11
4 | 2 | 1 | Group : join group created by someone else | Quentin | Terminé | 2022-05-07 | 11 | y | 1 | 2022-05-07 | 11
4 | 3 | 1 | Next movie page | Quentin | Terminé | 2022-05-07 | 11 | y | 1 | 2022-05-07 | 11
4 | 4 | 1 | Inputs Login & Register redesign error messages | Quentin | Terminé | 2022-05-07 | 11 | y | 1 | 2022-05-07 | 11
4 | 5 | 1 | Next movie page : display next movie highest rated by the group | Quentin | Terminé | 2022-05-08 | 12 | y | 1 | 2022-05-07 | 11
4 | 6 | 1 | Add movie modal : save movie to group | Quentin | Terminé | 2022-05-08 | 12 | y | 1 | 2022-05-07 | 11
4 | 7 | 1 | Group page : see group members | Martin | Terminé | 2022-05-08 | 12 | y | 1 | 2022-05-08 | 12
2 |  |  | Back-end : movie modal change request to imdb accordingly |  |  |  |  | n
2 |  |  | Register page : test page |  |  |  |  | n
|  |  | Back-end : search for a movie in db before calling imdb-api |  |  |  |  | n
|  |  | Back-end : creation of group and lists |  |  |  |  | n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
n
4 | 8 | 1 | Group page : see group details | Martin | Terminé | 2022-05-08 | 12 | y | 1 | 2022-05-08 | 12
4 | 9 | 1 | Next movie page : button to add new movie group | Quentin | Terminé | 2022-05-08 | 12 | y | 1 | 2022-05-08 | 12
4 | 10 | 1 | Voting page : change group | Quentin | Terminé | 2022-05-08 | 12 | y | 1 | 2022-05-08 | 12
4 | 11 | 1 | Voting page : button to add new movie to group | Quentin | Terminé | 2022-05-08 | 12 | y | 1 | 2022-05-08 | 12
4 | 12 | 1 | Voting page : see movies details by clicking on card | Quentin | Terminé | 2022-05-08 | 12 | y | 1 | 2022-05-08 | 12
4 | 13 | 1 | Next movie page : see movie detail by clicking on card | Quentin | Terminé | 2022-05-08 | 12 | y | 1 | 2022-05-08 | 12
4 | 14 | 1 | Next movie page : change group | Quentin | Terminé | 2022-05-08 | 12 | y | 1 | 2022-05-08 | 12
4 | 15 | 1 | Voting page : see movies by group that you haven't voted yet | Quentin | Terminé | 2022-05-08 | 12 | y | 1 | 2022-05-08 | 12
4 | 16 | 2 | Back-end : update movie rating | Julien | Terminé | 2022-05-07 | 11 | y | 2 | 2022-05-07 | 11
4 | 17 | 9 | Back-end : creation of group and lists | Julien | En cours | 2022-05-07 | 11 | y | 7 | 2022-05-07 | 11
4 | 18 | 10 | React Native Test Front | Kevin | En cours | 2022-05-09 | 13 | y | 4 | 2022-05-09 | 13
Storypoints |  | 36 | [5 empty] | Vélocité | 28

## Auxiliaire - Tableau Burndown
Storypoints
Jour de sprint | Courbe idéale | Courbe réelle | SP finis | Aktuell | Colonne1
0 | 33.4286 | 36 | 0 | y | 0
1 | 30.8571 | 36 | 0 | y | 0
2 | 30.8571 | 36 | 0 | y | 0
3 | 28.2857 | 36 | 0 | y | 0
4 | 25.7143 | 36 | 0 | y | 0
5 | 23.1429 | 36 | 0 | y | 0
6 | 20.5714 | 36 | 0 | y | 0
7 | 18 | 36 | 0 | y | 0
8 | 15.4286 | 36 | 0 | y | 0
9 | 12.8571 | 36 | 0 | y | 0
10 | 10.2857 | 36 | 0 | y | 0
11 | 7.7143 | 21 | 15 | y | 15
12 | 5.1429 | 12 | 9 | y | 11
13 | 2.5714 | 8 | 4 | y | 10
14 | 0 | 0 | 0 | n | 0
y
y
y
y
y
y
y
y
y
y
y
y
y
28