## DONNES
Date actuelle
2022-05-09
| Tâches | Début | Fin prévu | Fin réel | Statut | Nb jours prévu | Temps restant | Nb jours réel | Ecart de durée | Dépassement
Sprint 0 | Clarification fonctionnelle | 2021-12-07 | 2021-12-15 | 2022-01-04 | TERMINÉE | 8 | 0 | 28 | 2.5 | 250%
| Estimation | 2021-12-16 | 2021-12-22 | 2021-12-22 | TERMINÉE | 6 | 0 | 6 | 0 | 0%
| Attribution des rôles/Acteurs | 2021-12-23 | 2022-01-04 | 2022-01-04 | TERMINÉE | 12 | 0 | 12 | 0 | 0%
| Indicateurs | 2021-12-23 | 2022-01-04 | 2022-01-04 | TERMINÉE | 12 | 0 | 12 | 0 | 0%
| Risques | 2021-12-23 | 2022-01-04 | 2022-01-04 | TERMINÉE | 12 | 0 | 12 | 0 | 0%
| Proof of Concept | 2021-11-23 | 2022-01-04 | 2022-01-04 | TERMINÉE | 42 | 0 | 42 | 0 | 0%
Sprint 1 | Back-end : make a endpoint to get csrf token | 2022-01-06 | 2022-02-01 | 2022-01-23 | TERMINÉE | 26 | 0 | 17 | -0.34615 | -34.62%
| Back-end login | 2022-01-06 | 2022-01-17 | 2022-01-17 | TERMINÉE | 11 | 0 | 11 | 0 | 0%
| Back-end create new user | 2022-01-06 | 2022-01-17 | 2022-01-31 | TERMINÉE | 11 | 0 | 25 | 1.2727 | 127.3%
| Back-end : search for a movie in db before calling imdb-api | 2022-01-06 | 2022-01-24 |  | EN COURS | 18 | 0 | 123 | 5.8333 | 583.3%
| Registration page : create page | 2022-01-06 | 2022-01-17 | 2022-01-24 | TERMINÉE | 11 | 0 | 18 | 0.63636 | 63.64%
| Profil page | 2022-01-17 | 2022-01-24 |  | EN COURS | 7 | 0 | 112 | 15 | 1500%
| Add movie modal : see movie modal | 2022-01-06 | 2022-01-17 | 2022-01-17 | TERMINÉE | 11 | 0 | 11 | 0 | 0%
| Add movie modal : search movie by title | 2022-01-06 | 2022-01-17 | 2022-01-17 | TERMINÉE | 11 | 0 | 11 | 0 | 0%
| Groups : join / create group | 2022-01-06 | 2022-01-17 | 2022-01-17 | TERMINÉE | 11 | 0 | 11 | 0 | 0%
| Group page | 2022-01-17 | 2022-01-24 |  | EN COURS | 7 | 0 | 112 | 15 | 1500%
| Auth: check token and auto-relog | 2022-01-17 | 2022-02-01 | 2022-01-31 | TERMINÉE | 15 | 0 | 14 | -0.066667 | -6.667%
| Add movie : use modal | 2022-01-17 | 2022-02-01 |  | EN COURS | 15 | 0 | 112 | 6.4667 | 646.7%
| POC : finalize docker backend server with db | 2022-01-06 | 2022-02-01 | 2022-01-27 | TERMINÉE | 26 | 0 | 21 | -0.19231 | -19.23%
Sprint 2 | Group Page make prototype | 2022-02-01 | 2022-02-07 | 2022-02-07 | TERMINÉE | 6 | 0 | 6 | 0 | 0%
| Add movie modal : use modal | 2022-01-31 | 2022-02-17 | 2022-02-17 | TERMINÉE | 17 | 0 | 17 | 0 | 0%
| Registration page : validators for fields | 2022-02-01 | 2022-02-16 | 2022-02-16 | TERMINÉE | 15 | 0 | 15 | 0 | 0%
| Group page : Front | 2022-02-07 | 2022-02-28 | 2022-03-03 | TERMINÉE | 21 | 0 | 24 | 0.14286 | 14.29%
| Add movie modal : change group to assign movie to | 2022-02-01 | 2022-02-28 |  | EN COURS | 27 | 0 | 97 | 2.5926 | 259.3%
| Inputs : test inputs | 2022-02-01 | 2022-02-17 |  | EN COURS | 16 | 0 | 97 | 5.0625 | 506.2%
| Profil page | 2022-02-01 | 2022-02-20 | 2022-03-04 | TERMINÉE | 19 | 0 | 31 | 0.63158 | 63.16%
| Back-end : search for a movie in db before calling imdb-api | 2022-02-01 | 2022-02-17 | 2022-02-17 | TERMINÉE | 16 | 0 | 16 | 0 | 0%
Sprint 3 | Group Page : tab + header | 2022-03-05 | 2022-04-26 | 2022-04-15 | TERMINÉE | 52 | 0 | 41 | -0.21154 | -21.15%
| Project : adding Redux and refactoring | 2022-04-15 | 2022-04-20 | 2022-04-18 | TERMINÉE | 5 | 0 | 3 | -0.4 | -40%
| Input Login & Register : redesign error messages | 2022-03-05 | 2022-04-26 | 2022-04-18 | TERMINÉE | 52 | 0 | 44 | -0.15385 | -15.38%
| Movies : global state of movies and voted movies | 2022-03-05 | 2022-04-26 | 2022-04-18 | TERMINÉE | 52 | 0 | 44 | -0.15385 | -15.38%
| Home Page : Voting page | 2022-03-05 | 2022-04-26 | 2022-04-24 | TERMINÉE | 52 | 0 | 50 | -0.038462 | -3.846%
| Movie : MovieCard | 2022-03-05 | 2022-04-26 | 2022-04-24 | TERMINÉE | 52 | 0 | 50 | -0.038462 | -3.846%
| App : Themeing | 2022-03-05 | 2022-04-26 | 2022-04-19 | TERMINÉE | 52 | 0 | 45 | -0.13462 | -13.46%
| Register page : test page | 2022-03-05 | 2022-04-26 |  | EN COURS | 52 | 0 | 65 | 0.25 | 25%
| Inputs : test inputs | 2022-03-05 | 2022-04-26 |  | EN COURS | 52 | 0 | 65 | 0.25 | 25%
| Auth : test check token and auto-relog | 2022-03-05 | 2022-04-26 |  | EN COURS | 52 | 0 | 65 | 0.25 | 25% | Taux d'avancement Sprint en cours
| Add movie modal : change group to assign movie to | 2022-03-05 | 2022-04-26 |  | EN COURS | 52 | 0 | 65 | 0.25 | 25%
| Back-end : creation of group and list | 2022-03-05 | 2022-04-26 |  | EN COURS | 52 | 0 | 65 | 0.25 | 25%
| App : dark and light mode | 2022-03-05 | 2022-04-26 |  | EN COURS | 52 | 0 | 65 | 0.25 | 25%
Sprint 4 | Group page : see group movies | 2022-04-26 | 2022-05-07 | 2022-05-07 | TERMINÉE | 11 | 0 | 11 | 0 | 0% | 94%
| Group : join group created by someone else | 2022-04-26 | 2022-05-07 | 2022-05-07 | TERMINÉE | 11 | 0 | 11 | 0 | 0%
| Next movie page | 2022-04-26 | 2022-05-07 | 2022-05-07 | TERMINÉE | 11 | 0 | 11 | 0 | 0%
| Inputs Login & Register redesign error messages | 2022-04-26 | 2022-05-07 | 2022-05-07 | TERMINÉE | 11 | 0 | 11 | 0 | 0%
| Next movie page : display next movie highest rated by the group | 2022-04-26 | 2022-05-08 | 2022-05-08 | TERMINÉE | 12 | 0 | 12 | 0 | 0%
| Add movie modal : save movie to group | 2022-04-26 | 2022-05-08 | 2022-05-08 | TERMINÉE | 12 | 0 | 12 | 0 | 0%
| Group page : see group members | 2022-04-26 | 2022-05-08 | 2022-05-08 | TERMINÉE | 12 | 0 | 12 | 0 | 0%
| Group page : see group details | 2022-04-26 | 2022-05-08 | 2022-05-08 | TERMINÉE | 12 | 0 | 12 | 0 | 0%
| Next movie page : button to add new movie group | 2022-04-26 | 2022-05-08 | 2022-05-08 | TERMINÉE | 12 | 0 | 12 | 0 | 0%
| Voting page : change group | 2022-04-26 | 2022-05-08 | 2022-05-08 | TERMINÉE | 12 | 0 | 12 | 0 | 0%
| Voting page : button to add new movie to group | 2022-04-26 | 2022-05-08 | 2022-05-08 | TERMINÉE | 12 | 0 | 12 | 0 | 0%
| Voting page : see movies details by clicking on card | 2022-04-26 | 2022-05-08 | 2022-05-08 | TERMINÉE | 12 | 0 | 12 | 0 | 0%
| Next movie page : see movie detail by clicking on card | 2022-04-26 | 2022-05-08 | 2022-05-08 | TERMINÉE | 12 | 0 | 12 | 0 | 0%
| Next movie page : change group | 2022-04-26 | 2022-05-08 | 2022-05-08 | TERMINÉE | 12 | 0 | 12 | 0 | 0%
| Voting page : see movies by group that you haven't voted yet | 2022-04-26 | 2022-05-08 | 2022-05-08 | TERMINÉE | 12 | 0 | 12 | 0 | 0%
| Back-end : update movie rating | 2022-04-26 | 2022-05-07 | 2022-05-07 | TERMINÉE | 11 | 0 | 11 | 0 | 0%
| Back-end : creation of group and lists | 2022-04-26 | 2022-05-07 | 2022-05-07 | TERMINÉE | 11 | 0 | 11 | 0 | 0%
| React Native Test Front | 2022-04-26 | 2022-05-09 |  | EN COURS | 13 | 0 | 13 | 0 | 0%
| Tâches | Début | Fin prévu | Fin réel | Statut | Nb jours prévu | Temps restant | Nb jours réel | Ecart de durée | Dépassement
Nb jours avant la fin du Sprint 0 : 0
Nb jours avant la fin du Sprint 1 : 0
Nb jours avant la fin du Sprint 2 : 0
Nb jours avant la fin du Sprint 3 : 0
Group page : see group details
Next movie page : button to add new movie group
Voting page : change group
Voting page : button to add new movie to group
Voting page : see movies details by clicking on card
Next movie page : see movie detail by clicking on card
Next movie page : change group
Voting page : see movies by group that you haven't voted yet
Back-end : update movie rating
Back-end : creation of group and lists
React Native Test Front
Formulas:
Nb jours prévu = DATEDIF([Début],[Fin prévu],"d")
Temps restant = IF([Fin prévu]<A2,0,DATEDIF(A2,[Fin prévu],"d"))
Nb jours réel = IF(ISBLANK([Fin réel]),DATEDIF([Début],A2,"d"),DATEDIF([Début],[Fin réel],"d"))